## Oct16
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-10-25 | Tuesday | Ankush | Started working on Notifications | Document upload - Notifications | EOD
|  | Navin | Tested Support document functionality Created one account on live Live IB form regression testing | 1. Testing Questionnaire issues 2. Daily tasks | 1. 1/2 Hrs 2.
|  | Nilesh | PHP Basics | 1. Ajax - W3school 2. Assignment
|  | Rafat |  |  |  |  | Absent
|  | Tabassum |  | 1. Designing Monthly reports 2. Pricing page design | 1. 2 Hrs 2. | Machines problem
|  | Tejashree | Acc settings & Notification | 1. Will finish Notification & issues raisded by Navin 2. Design issues - Acc settings, Raised in mantis |  | Need updation on Recommendation designs
2016-10-26
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-10-27 | Tuesday | Ankush | Document upload - Notifications | Notification Popup Separate page for listing |  | HTML design Monthly reports
|  | Navin | Live - created account Regression testing - IB form User restriction | Retake - Clientportal testing on dev User restriction testing on live |  | Support docs UAT on live UAT user restriction on live
|  | Nilesh | Assignment - Completed form design | Working on functionality DB connection issue Edit form | EOD
|  | Rafat | Absent | 1. Acc testing issues need to solved raised by Navin 2. Email responsive changes 3. change email as per dev enviorment 4. Email templates listing for Admin |  | Acc setting discussion with Roshan/Bhavank Add fund & withdrwa fund popup discussion with Bhavank Acc setting History discussion
|  | Tabassum | Monthly Report completed | Brouchers | Tomorrow EOD | Need contetnt from Akram Why wahed Design approval
|  | Tejashree | 1. Solved IB form issue 2. Design issue - Acc settingd | 1. Portfolio page changes 2. Bhavank design issues 3. Monthly report - HTML |  | Need approval on Recommendation designs Portfolio page merging approval
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-10-28 |  | Ankush | Notification - Linking document functionality - Pending Popup - Done Separate page for listing - Pending | Notification - Linking document functionality - Pending Separate page for listing - Pending | EOD
|  | Navin | Retake - Clientportal testing on dev - Done User restriction testing on live - Done | IB form testing Acc settings testing Notification testing | EOD
|  | Nilesh | Assignment - Edit, bootstrap design | Edit will be done Assignment - | EOD
|  | Rafat | 1. Acc testing issues need to solved raised by Navin - 2. Email responsive changes - Done 3. change email as per dev enviorment - Pending 4. Email templates listing for Admin - Pending | 1. Acc testing issues need to solved raised by Navin - 2. IB form changes given by me 3. change email as per dev enviorment - Pending
|  | Tabassum | Brouchers | Brouchers | EOD | Waiting for content from Akram
|  | Tejashree | 1. Portfolio page changes, image changes - Done 2. Bhavank design issues - Pending 3. Monthly report - HTML - Pending 4. Got feedback from Juanid on Recommendation page & Why wahed. | 1. Notification desgin changes 2. Bhavank design issues | EOD | Portfolio page images are changes, need approval.

## Nov16
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-01 |  | Ankush |  |  |  |  | Absent
|  | Navin | IB form testing Acc settings testing Notification testing | 1. Acc setting testing 2. Emails responsiveness testing 3. Notification testing | 1. EOD 2. EOD
|  | Nilesh | Edit will be done Assignment - | Assignment - | EOD
|  | Rafat | 1. Acc testing issues need to solved raised by Navin - 2. IB form changes given by me 3. change email as per dev enviorment - Pending | 1. change email as per dev enviorment - Pending 2. Email templates for Admin 3. Blank name in Welcome emails
|  | Tabassum | Brouchers | Brouchers | Deadline - EOD
|  | Tejashree | 1. Notification desgin changes 2. Bhavank design issues | 1. Junaid mails - positions tab 2. Press release page 3. Account settings design issues |  |  | 1. DONE 2. DONE 3. DONE
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-02 |  | Ankush |  |  |  |  | Absent
|  | Navin | 1. Press release tested 2. | Acc setting & Retake quiz regression testing in all resolutions | EOD
|  | Nilesh | Assignment - | Assignement improvements
|  | Rafat | 1. Solved issue in withdrw fund functionality | 1. Print - RnD 2. Email templates 3. Operations tab - Document shared / Document signed
|  | Tabassum | Brouchers | Got new requirment from Juanid | Deadline - EOD | Need Approval on why wahed design
|  | Tejashree | 1. Junaid mails - positions tab 2. Press release page 3. Account settings design issues | 1. Recommendation page 2. About Us - Why wahed 3. Pricing page - As per Tabassum stop this 4. Why wahed 5. Investment methodology 6. Datatable replacement 7. Mantis design issues
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-03 |  | Ankush
|  | Navin | Acc setting & Retake quiz regression testing in all resolutions | Acc settings & retake - retest Document & notification functionality IB form testing - IRA account link
|  | Nilesh | Assignement improvements | Assignement improvements
|  | Rafat | 1. Print - RnD 2. Email templates 3. Operations tab - Document shared / Document signed 4. Admin & normal user left panel 5. Issues related to footer | 1. Retake quiz - Recommended portfolio. 2. My profile changes - If IB form not filled 3. Email templates
|  | Tabassum | Brouchers - Got new requirment from Juanid | Brouchers - Got new requirment from Juanid
|  | Tejashree | 1. Acc settings issues raised by Navin | 1. Design changes suggested by junaid - Positions page graph 2. Retake quiz - Design changes
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-04 |  | Ankush
|  | Navin | Acc settings & retake - retest Document & notification functionality IB form testing - IRA account link | Acc settings & retake Live regression testing
|  | Nilesh | Assignement improvements | Changes given by Sandeep | EOD
|  | Rafat | 1. Retake quiz - Recommended portfolio. 2. My profile changes - If IB form not filled IB form - Fanancial info issue solved which was raised In mantis Left panel - border bottom Changes given by Junaid RnD on print Deposit conformation mobile devices | Print functionlity on mobile Admin email templates Retake quiz functionality modification |  | Retake quiz functionality modification - Sandeep
|  | Tabassum | Brouchers - Got new requirment from Juanid | Brouchers is completed Can start working on Investment methodology design About us - Why wahed HTML |  | Why wahed - waiting for design approval
|  | Tejashree | 1. Design changes suggested by junaid - Positions page graph 2. Retake quiz - Design changes | 1. Retake quiz - recommendation page responsive issue 2. Positions page graph Changes | 1. EOD | Design changes suggested by junaid - Positions page graph - Need help from Ankush
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-07 |  | Ankush | 1 | 1. Documents & Notifications issues raised by Navin 2. Notifications design
|  | Navin | Acc settings & retake Live regression testing | Acc settings & retake Live regression testing IB form design - regression testing Print functionlaity testing done by Rafat Document notification testing | All EOD
|  | Nilesh | Changes given by Sandeep | Reading CI
|  | Rafat | Print functionlity on mobile Admin email templates Retake quiz functionality modification | 1. Print functionality Testing 2. Admin email templates | 1. EOD | Retake quiz functionality modification - Sandeep
|  | Tabassum | Brouchers is completed Can start working on Investment methodology design About us - Why wahed HTML Installing SVN whole day | 1. Broucher changes - Update background 2. Investment methodology need design approval to start its HTML About us - Why wahed is part of about us, need to discuss and design its tab design | 1. EOD 2. EOD | 1. Why wahed - waiting for design approval 2. Investment methodology approval 3. Will need help from Anksuh for Jquery - Investment ethodology page
|  | Tejashree | 1. Retake quiz - recommendation page responsive issue 2. Positions page graph Changes | 1. Retake quiz - recommendation page responsive issue 2. Positions page graph Changes 3. Notifications design | 1. EOD 2. EOD | Design changes suggested by junaid - Positions page graph - Need help from Ankush
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-08 |  | Ankush | 1. Documents & Notifications issues raised by Navin 2. Notifications design | 1. Chnages in displaying notification list | 1. Before lunch
|  | Navin | Acc settings & retake Live regression testing IB form design - regression testing Print functionlaity testing done by Rafat Document notification testing | 1. Acc settings mobile testing
|  | Nilesh | Reading CI | Reading CI
|  | Rafat | 1. Print functionality Testing - DONE 2. Admin email templates - In progress | 1. Print functionality given forTesting 2. Admin email templates - In progress
|  | Tabassum | 1. Broucher changes - Update background 2. Investment methodology need design approval to start its HTML About us - Why wahed is part of about us, need to discuss and design its tab design | 1. Broucher changes done sent for Approval 2. HTML - Investment methodology | 2. EOD
|  | Tejashree | 1. Retake quiz - recommendation page responsive issue - DONE 2. Positions page graph Changes 3. Notifications design - DONE | 1. Position page graph changes 2. Notification - Mobile show count for notifications & other issues raised by Navin 3. Datatables - Deisgn changes 4. Acc settings design issues if any
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-09 |  | Ankush
|  | Navin | 1. Acc settings mobile testing | 1. Acc settings & Retake quiz live regression testing 2. Portfolio page testing on website | EOD
|  | Nilesh | Reading CI Javascript changes given by Sandeep | Javascript & Ajax changes | EOD
|  | Rafat | 1. Print functionality given forTesting 2. Admin email templates - In progress 3. Acc settining - Retake quiz & withdrwa functionality changes are done | 1. DONE 2. In progress
|  | Tabassum | 1. Broucher changes done sent for Approval 2. HTML - Investment methodology | 1. DONE 2. EOD | 2. EOD
|  | Tejashree | 1. Position page graph changes 2. Notification - Mobile show count for notifications & other issues raised by Navin 3. Datatables - Deisgn changes 4. Acc settings design issues if any | 1. Retake quiz radio button issue 2. Portfolio make live 3. Positions page 4. Notification count in mobile | 1. EOD 2. EOD 3. EOD 4. EOD
2016-11-10 | No meeting
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-11 |  | Ankush | 1. Chnages in displaying notification list | 1. Document 2. Operations - App request 3. Notification bugs | 1. EOD 2. EOD 3. EOD
|  | Navin |  | Regression Testing on Live Document Operations Notifications Acc settings & Retake quiz |  |  | Absent
|  | Nilesh | Javascript & Ajax changes | Javascript & Ajax changes
|  | Rafat | 1. Solved 5 bugs from mantis 2. Email listing is done. 3. Working on Compose emails | 2. Given for testing 3. EOD
|  | Tabassum | 1. Broucher changes done sent for Approval 2. HTML - Investment methodology | 1. DONE 2. Scroll issue & Responsive design 3. Started working on Why wahed | 2. EOD
|  | Tejashree | 1. Retake quiz radio button issue 2. Portfolio make live 3. Positions page 4. Notification count in mobile | 1. Recommendation page background changes 2. Design issues - Left nevigation, font changes 3. Operations tab - Datatables issue(Ankush) 4. Design issues logged by Navin
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-16 |  | Ankush | 1. Started Monthly reports | Monthly report | EOD | Bhavank & Akram discussion
|  | Navin | 1. Wesite testing Portfolio whole testing | 1. Document, Notification & operations regression testing | EOD
|  | Nilesh | Reading CI |  | End of this week
|  | Rafat | 1. Working on Compose emails | 1. Compose email - Custom email subject | EOD
|  | Tabassum | 1. Investment methodolofy completed 2. Recommendation page design option 3. Issue raised by Navin Wrap fee broucher - Logo & number | 1. Creating multiple logos 2. About - Why wahed |  | Investment methodology - position fixed issue
|  | Tejashree | 1. Recommendation page HTML | 1. Recommendation page HTML Website
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-17 |  | Ankush | Monthly report | 1. Operations - issues raised by Bhavank 2. Notification & Document issues raised by Navin | EOD
|  | Navin | 1. Document, Notification & operations regression testing | 1. Operations 2. Compose email functionality on dev server
|  | Nilesh | CI implementation of assignment | Javascript validation in admin form
|  | Rafat | 1. Compose email - Custom email subject | 1. Resend - email functionality. 2. User Activity log
|  | Tabassum | 1. Creating multiple logos 2. About - Why wahed | 1. About - Why wahed | EOW
|  | Tejashree | 1. Recommendation page HTML Website | 1. Operations - right & left margin issue in bhavanks desktop 2. Monthly report - HTML for download and email 3. Recommendation page - accordian issue 4. Mantis design issues
|  | Sandeep | 1. Tradelineup - Saving trade into files 2. Investment methodology - Sidebar position fixed | 1. Assign mantis issue 2. Tradelineup - Saving trade into files 3. Investment methodology - Sidebar position
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-17 |  | Ankush | 1. Operations - issues raised by Bhavank 2. Notification & Document issues raised by Navin | 1. Operations - issues raised by Bhavank 2. Notification & Document issues raised by Navin | EOD |  | Deadline missed Helped Tabassum & Tejashree
|  | Navin | 1. Operations 2. Compose email functionality on dev server | 1. Logo click - Open website in new tab 2. Document, Notification & Operations retest after issue solved by Navin
|  | Nilesh | Javascript validation in admin form | Ajax validation In progress | EOD
|  | Rafat | 1. Resend - email functionality. 2. User Activity log | 1. Done 2 User activity inprogress |  | Need to discuss User activity functionlity with Roshan and Sandeep
|  | Tabassum | 1. About - Why wahed | 1. Investment methodology - Content changes on hold 2. About - Why wahed in progress | 2. End of Monday
|  | Tejashree | 1. Operations - right & left margin issue in bhavanks desktop 2. Monthly report - HTML for download and email 3. Recommendation page - accordian issue 4. Mantis design issues | 3. Recommendation page design Geographic content will be pending | EOD
|  | Sandeep | 1. Assign mantis issue 2. Tradelineup - Saving trade into files 3. Investment methodology - Sidebar position | 1. Assign mantis issue 2. Tradelineup - Saving trade into files 3. Internal discussion with Roshan - Apex 4. Meeting with Babu - Apex 5. Activity log discussion - Rafat & Akram
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-21 |  | Ankush | 1. Operations - issues raised by Bhavank 2. Notification & Document issues raised by Navin | 1. Operations issues raised by bhavank are done except one Design issues are pending 2. Mantis issues solved 3. Plugins issues are pending 4. Data tables - Sort by date issue 5. EST - Time zone issue
|  | Navin | 1. Logo click - Open website in new tab 2. Document, Notification & Operations retest after issue solved by Navin | 1. Operations , document & Notification testing on dev server 2. Mantis bugs retesting
|  | Nilesh | Ajax validation In progress | Roshan will give intro to user registration & Client Portal
|  | Rafat | 1. Done 2 User activity inprogress | 1. User activity log progress
|  | Tabassum | 1. Investment methodology - Content changes on hold 2. About - Why wahed in progress | 1. Working on About page - Why wahed | Tomorrow EOD
|  | Tejashree | 3. Recommendation page design - DONE Geographic content will be pending | 1. Recommendation page - Geographic content 2. Operations page - Design issues 3. Datatable issues - Clientportal 4. Monthly reports | 1 & 2 EOD
|  | Sandeep | 1. Assign mantis issue 2. Tradelineup - Saving trade into files 3. Internal discussion with Roshan - Apex 4. Meeting with Babu - Apex 5. Activity log discussion - Rafat & Akram
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-28 |  | Ankush | 1. Operations issues raised by bhavank are done except one Design issues are pending 2. Mantis issues solved 3. Plugins issues are pending 4. Data tables - Sort by date issue 5. EST - Time zone issue ------------------------------------------------ Recommendation page design given by Junaid | Apex - Legit Recommendation page design issues
|  | Navin | 1. Operations , document & Notification testing on dev server 2. Mantis bugs retesting -------------------------------------- IB form regression testing Clientportal Admin | Website - About page done by Tabbassum
|  | Nilesh | Roshan will give intro to user registration & Client Portal Apex docs | Clientportal & Website SVN checkout
|  | Rafat | 1. User activity log progress - Pending with listing rest is done | APEX - Legit API
|  | Tabassum | 1. Working on About page - Why wahed Done with why wahed, need to upload on dev server | Started with monthly reports |  |  | Came late
|  | Tejashree | 1. Recommendation page - Geographic content 2. Operations page - Design issues 3. Datatable issues - Clientportal 4. Monthly reports | Recommendation page design issues Left nevigation, and data tables issues
|  | Sandeep | Etnatrader - APIs explored | APEX - Legit API About us page design need to be uploaded on dev server committed by Tabassum
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-29 |  | Ankush | Apex - Legit Recommendation page design issues | APEX - Legit API
|  | Navin | Website - About page done by Tabbassum | Admin regression testing issues raised in mantis
|  | Nilesh | Clientportal & Website SVN checkout | Going through code - Clientportal & Website
|  | Rafat | APEX - Legit API | APEX - Legit API
|  | Tabassum | Started with monthly reports | Monthly report - Working on first page
|  | Tejashree | Recommendation page design issues Left nevigation, and data tables issues | Recommendation page design issues - Show/hide description Two tabs - Expected Returns & Past Performance Left nevigation, and data tables issues
|  | Sandeep | APEX - Legit API About us page design need to be uploaded on dev server committed by Tabassum | About us page design need to be uploaded on dev server |  | Need list of files from tabassum to put on dev server
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-11-30 |  | Ankush | APEX - Legit API | Apex - Account creation API Recommendation page - past performance tab Zip code API - Will be done today
|  | Navin | Admin regression testing issues raised in mantis |  |  |  | Absent
|  | Nilesh | Going through code - Clientportal & Website | List down controllers, functions, helpers, models & view for Clientportal and Website
|  | Rafat | APEX - Legit API | New IB form as per new wireframes
|  | Tabassum | Monthly report - Working on first page |  |  |  | Absent
|  | Tejashree | Recommendation page design issues - Show/hide description Two tabs - Expected Returns & Past Performance Left nevigation, and data tables issues | Recommendation page - Past performance Tab will be done today.
|  | Sandeep | About us page design need to be uploaded on dev server | Apex - Account creation API New questionnaire - as per roshans wireframe

## Dec16
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-01 |  | Ankush | APEX - Legit API | Apex - Account creation API Recommendation page - past performance tab is done, working on expected return Zip code API - Done
|  | Navin | Admin regression testing issues raised in mantis | 1. Writing test scenarios for new APEX form 2. Writing test cases for Questionnaire
|  | Nilesh | Going through code - Clientportal & Website | Will solve mantis issue today
|  | Rafat | APEX - Legit API | New IB form as per new wireframes
|  | Tabassum | Monthly report - Working on first page | Working on - Monthly reports, only web interface PDF will be done by Developers
|  | Tejashree | Recommendation page design issues - Show/hide description Two tabs - Expected Returns & Past Performance Left nevigation, and data tables issues | Recommendation page - Past performance Tab will be done today.
|  | Sandeep | About us page design need to be uploaded on dev server | Apex - Account creation API New questionnaire - as per roshans wireframe Create one manstis user for Nilesh
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-05 |  | Ankush | Apex - Account creation API Recommendation page - past performance tab is done, working on expected return Zip code API - Done | Apex - all APIs calls
|  | Navin | 1. Writing test scenarios for new APEX form 2. Writing test cases for Questionnaire | Apex form testing across browsers.
|  | Nilesh | Will solve mantis issue today | Testing New Apex form and Questionnaire
|  | Rafat | New IB form as per new wireframes | New Apex form issues raised by Navin
|  | Tabassum | Working on - Monthly reports, only web interface PDF will be done by Developers | Working on Monthly reports. Monthly reports web layout |  | Need help from Ankush for graphs
|  | Tejashree | Recommendation page - Past performance Tab will be done today. | 1. Questionnaire and Aprx form Success message need to be change. 2. Recommendation responsive issue 3. age text filed hand cursor |  | Ask akram about emailer
|  | Sandeep | Apex - Account creation API New questionnaire - as per roshans wireframe Create one manstis user for Nilesh | 1. Create schema for Apex
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-08 |  | Ankush | Apex - Plaid and ACH api calls | Will continue plaid and ACH APIs
|  | Navin | Apex form and Questionnaire testted on IOS | Will test both on firebox - Live
|  | Nilesh | Testing New Apex form and Questionnaire | Testing New Apex form and Questionnaire
|  | Rafat | Apex form added calender, Masking code added its on development | Need to start with Apex APIs Need to solve Apex form issue
|  | Tabassum | Working on Monthly reports. Monthly reports web layout |  |  |  | Absent
|  | Tejashree | 1. Recommendation page - Responsiveness changes. Changed Tabs. | 1. Recommendatio page will be done today. 2. Success page designs
|  | Sandeep | 1. Create schema for Apex 2. Importing SOD files from Apex sftp | 1. Integrate SOD files functionality in CI
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-09 |  | Ankush | Will continue plaid and ACH APIs |  |  |  | Absent
|  | Navin | Will test both on firebox - Live | Recommendation page testing on dev
|  | Nilesh | Testing New Apex form and Questionnaire | Recommendation page testing on dev Login issue - 542
|  | Rafat | Need to start with Apex APIs Need to solve Apex form issue | Apex form issues solved Apex - account create - schema generation
|  | Tabassum | Monthly report web page is done except graph |  |  | Need help from Ankush for graphs
|  | Tejashree | 1. Recommendatio page will be done today. 2. Success page designs | Recommnedation is done, need to test Started working on success page
|  | Sandeep | 1. Integrate SOD files functionality in CI
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-12 | No Meetring
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-13 |  | Ankush |  |  |  |  | Absent
|  | Navin | Recommendation page testing on dev | 1. New Apex form opening on dev server 2. Funding of accounts on dev server 3. Create excel sheet for font cross browser comaptibility
|  | Nilesh | Recommendation page testing on dev Login issue - 542 | Login form JS issue
|  | Rafat | Apex - account opening with JSON is done | Account opening testing on dev
|  | Tabassum | Working on top nevigation Website font-size issue raised by Junaid | 1. Top nevigation design 2. Create excel sheet for font cross browser comaptibility 3. Pricing page graph |  | Need to discuss same with Akram | Need specific pages where font-size is different
|  | Tejashree | success page is done | Clientportal left nevigation - Slide
|  | Sandeep | Worked on SOD files data | 1. Create FTP for new Apex form 2. Calulations for Overview, positions and Transactions page 3. New Recommendation page - select this portfolio functionality
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-14
No meeting
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-13 |  | Ankush |  | Create php code for Sketch/Snap Change url - questionnaire
|  | Navin | 1. Apex form regression testing on chrome 2. Create excel sheet for font cross browser comaptibility | Apex form testing on UAT
|  | Nilesh | Login form JS issue UAT testing, Apex form testing | Sample code - CURL request
|  | Rafat | Account opening testing on dev | Account Update After account opening save status of accout in table, run cron to check status, on success shoot email to User & Admin |  | Which fields to edit need to confirm with operations - Roshan
|  | Tabassum | 1. Top nevigation design 2. Create excel sheet for font cross browser comaptibility 3. Pricing page graph | Working on Top menu Font changes on Website Pricing page design suggested by Akram |  | Need to discuss same with Akram | Need specific pages where font-size is different
|  | Tejashree | Clientportal left nevigation - Slide | About us page changes given by Junaid Textual changes on website Pricing page - Given by Junaid & Akram
|  | Sandeep | 1. Create FTP for new Apex form 2. Calulations for Overview, positions and Transactions page 3. New Recommendation page - select this portfolio functionality | Go through doc given by Navin for font changes SOD files calculations
|  |  | Open issue | Wire withdrwal
|  |  | Open issue | Tale - not authorised
EXT868 - Sample position and trade dump SOD files - Not getting at Sftp
are we going to store data in DB ex SSN
Account creation - what if we get error for account creation - new request - Operatations will handle
Date | Day | Resource | Yesterdays task | Currenntly working on | Deadline | impediment | Remarks
2016-12-13 |  | Ankush | Create php code for Sketch/Snap Change url - questionnaire |  |  |  | Absent
|  | Navin | Apex form testing on UAT | Apex form testing on UAT
|  | Nilesh | Sample code - CURL request | CI new project,
|  | Rafat | Account Update After account opening save status of accout in table, run cron to check status, on success shoot email to User & Admin | 1. UI - Apex account update 2. After account opening save status of accout in table, run cron to check status, on success shoot email to User & Admin
|  | Tabassum | Working on Top menu - DONE Font changes on Website Pricing page design suggested by Akram | About page - advisory page section Font size changes |  |  | Need specific pages where font-size is different
|  | Tejashree | About us page changes given by Junaid Textual changes on website Pricing page - Given by Junaid & Akram | Pricing page changes given by Junaid |  | Need to discuss new pricing page design with Akram
|  | Sandeep | Go through doc given by Navin for font changes SOD files calculations | Website top menu - upload on live Upload Apex form files on live